## Overview
Zurvival Reborn — Scope-Control Tracker
The living operational layer of PRODUCTION.md. Solo + AI · effort-based · the "no machine".
HOW TO USE THIS BOOK
Milestones | M0–M5 ladder + post-launch. % complete auto-computes from the Backlog. Theme, gate, and risk-retired per milestone.
Backlog | Every PRD requirement as a work item, mapped to milestone, MoSCoW, the principle it serves, effort, and AI-assist. This is the work.
Content Budget | Caps per milestone that protect REVIEW CAPACITY. Set "Current milestone"; a red Headroom cell = stop authoring, go playtest.
Risk Burn-down | Each PRD risk mapped to the milestone that retires it. Update status as you go.
Decision Gates | Open ADRs, each tied to the milestone it must be resolved by. ADR-0001 is the one to force at M0.
Parking Lot | New ideas land here — never in a live milestone. Triage only at boundaries. Pre-seeded with the frozen Won’t-now register.
Fun-Gate Log | Every gate verdict: build, date, the retellable moment, go/no-go. The gate is the point.
THE CUT FILTER — the "no machine"
The rule | A feature must serve ≥ 1 of the six principles. If it serves none, it WAITS or DIES. If it serves one but costs more review capacity than the milestone budget allows, it DEFERS.
P1 | A systemic core loop
P2 | Injuries are stories
P3 | Nodes with memory
P4 | The Survival Triangle (Safety · Resources · Time)
P5 | Handcrafted social simulation
P6 | Artifacts over XP
LEGEND
MoSCoW | Must = milestone not done without it (never cut to hit a date) · Should = cut first · Could = only if ahead · Won’t = frozen
Cut order under pressure | Coulds → Shoulds → re-scope the milestone. NEVER cut a Must or skip a fun gate.
Status colours | Done = green · In progress = amber · Blocked = red · Not started = grey · Cut = struck through
Effort bands | XS <½ wk · S ~1 wk · M ~2–3 wk · L ~4–6 wk · XL ~8+ wk (solo + AI; re-calibrate after M1). >25% over band = scope-review tripwire.

## Milestones
Milestone Ladder
Numbering follows the PRD (M1–M5) + explicit M0 Foundation. % auto-computes from Backlog status.
ID | Milestone | Theme | Horizon | Effort | % done | Fun gate | Risk retired | Definition of done (short)
M0 | Foundation | The skeleton runs | pre-VS | M | 0% | — | Undecided stack / paralysis | Deterministic core runs the full pipeline; save round-trips; CI rejects malformed content.
M1 | Core loop playable | The loop is satisfying | Vertical Slice | L | 0% | Loop-Feel Check | (loop-feel read) | A slice of turns runs end-to-end; every turn changes ≥1 system; stealth path exists; lossless resume.
M2 | Reactive world | The world moves on its own | Vertical Slice | L | 0% | — | Impressive but static | Region threat shifts off-screen; gunshot re-paths a horde; director biases without breaking logic.
M3 | People, shelter & first story | A run becomes a story | Vertical Slice — complete | XL | 0% | SLICE FUN GATE (decisive) | Systemic but not fun | A full slice run yields an emergent, retellable story; companion fate lands; shelter loss is survivable.
M4 | Content-complete city | Breadth without repetition | MVP / public beta | XL | 0% | — | Content volume | One city content-complete & schema-valid; repeat-rate under target; infection-as-identity comprehensible.
M5 | Release candidate | Balanced, accessible, hardened | v1.0 launch | XL | 0% | "one more day" w/ externals | Balance fragility · save churn | Every Must met; balance targets hit; save survives migration; accessibility verified with assistive tech.
P+ | Post-launch | Content cadence + new clients | live | ongoing | — | — | Long-tail relevance | Expansion-hook content needing no engine rewrite; then native & chat-bot clients (ADR-0004).
Gate rule: if the Slice Fun Gate (M3) fails, scope re-invests in the loop/characters — content stays frozen. Never "add content" to fix fun.

## Backlog
Backlog
Every PRD requirement as a work item. Traces to the PRD by ID. Filter by Milestone / MoSCoW / Status.
ID | Area | Requirement | Milestone | MoSCoW | Type | Serves | Effort | AI-assist | Status | DoD met | Notes
PROD-01 | Foundation | ADR-0001: choose engine language & runtime (time-boxed) | M0 | Must | Decision | P1 | S | No | Not started | No
PROD-02 | Foundation | GameState shape + turn-pipeline shell (14 stages) | M0 | Must | Engine | P1 | M | Yes | Not started | No
PROD-03 | Foundation | Seeded RNG with named streams, serialized with state | M0 | Must | Engine | P1 | S | Yes | Not started | No
PROD-04 | Foundation | Content loader + first schemas | M0 | Must | Engine | P1 | M | Yes | Not started | No
PROD-05 | Foundation | CI: malformed content fails the build | M0 | Must | Infra | P1 | S | Yes | Not started | No
PROD-06 | Foundation | Determinism / golden-run test harness | M0 | Must | QA | P1 | M | Yes | Not started | No
PROD-07 | Foundation | Terminal harness runs an empty turn | M0 | Must | Client | P1 | S | Yes | Not started | No
FR-CNT-01 | Content pipeline | Content authored as external data, loaded at runtime | M0 | Must | Engine | P1 | M | Yes | Not started | No
FR-CNT-02 | Content pipeline | Content validated vs schemas in CI | M0 | Must | Infra | P1 | S | Yes | Not started | No
NFR-PLAT-02 | Platform | Headless / renderer-agnostic engine | M0 | Must | Engine | P1 | M | Yes | Not started | No
FR-CORE-01 | Core loop | Turn loop, no direct choice→scene edge | M1 | Must | Engine | P1 | M | Yes | Not started | No
FR-CORE-02 | Core loop | Fixed pipeline order executed every turn | M1 | Must | Engine | P1 | S | Yes | Not started | No
FR-CORE-03 | Core loop | Every action has a time cost | M1 | Must | Engine | P4 | S | Yes | Not started | No
FR-CORE-04 | Core loop | Every resolved action changes ≥1 system | M1 | Must | Engine | P1 | S | Yes | Not started | No
FR-CORE-05 | Core loop | Scenes answer the Four Questions | M1 | Must | Design | P1 | S | No | Not started | No
FR-CORE-07 | Core loop | Safe-to-stop autosave at turn boundary | M1 | Must | Engine | P1 | S | Yes | Not started | No
FR-SIM-02 | World sim | Local-area node memory persists all run | M1 | Must | Engine | P3 | M | Yes | Not started | No
FR-SIM-04 | World sim | Time-of-day phases modify odds/visibility | M1 | Must | Engine | P4 | S | Yes | Not started | No
FR-SIM-06 | World sim | Noise model: emit / attract / decay | M1 | Must | Engine | P1 | M | Yes | Not started | No
FR-MAP-01 | Exploration | Node graph grouped into regions | M1 | Must | Engine | P3 | M | Yes | Not started | No
FR-MAP-02 | Exploration | Fog of war: only known nodes revealed | M1 | Must | Engine | P3 | S | Yes | Not started | No
FR-MAP-03 | Exploration | Travel costs time/stamina/noise | M1 | Must | Engine | P4 | S | Yes | Not started | No
FR-PLR-01 | Player | Persistent player state | M1 | Must | Engine | P6 | M | Yes | Not started | No
FR-PLR-02 | Player | Only a critical few visible stats | M1 | Must | UI | P4 | S | No | Not started | No
FR-PLR-03 | Player | Weight/slot-limited inventory | M1 | Must | Engine | P4 | S | Yes | Not started | No
FR-PLR-04 | Player | Equipment defines capability (not levels) | M1 | Must | Engine | P6 | M | Yes | Not started | No
FR-PLR-10 | Player | No XP bar or character level anywhere | M1 | Must | Design | P6 | XS | No | Not started | No
FR-INJ-01 | Injuries | Damage produces named wounds | M1 | Must | Engine | P2 | M | Yes | Not started | No
FR-INJ-04 | Injuries | Health is treated, not auto-regenerated | M1 | Must | Engine | P2 | S | Yes | Not started | No
FR-ENC-01 | Encounters | Tagged pool filtered by requirements engine | M1 | Must | Engine | P1 | M | Yes | Not started | No
FR-ENC-02 | Encounters | Weighting + cooldowns favour fresh content | M1 | Must | Engine | P1 | M | Yes | Not started | No
FR-CBT-01 | Combat | Combat avoidable; always spends resources | M1 | Must | Engine | P4 | M | Yes | Not started | No
FR-CBT-02 | Combat | Turn-based exchange vs systems, not twitch | M1 | Must | Engine | P1 | M | Yes | Not started | No
FR-CBT-04 | Combat | Weapon categories; firearms are loud | M1 | Must | Engine | P4 | S | Yes | Not started | No
FR-CBT-05 | Combat | Stealth via sound/light/LoS detection | M1 | Must | Engine | P4 | M | Yes | Not started | No
FR-ECO-01 | Economy | Finite, contested loot; taking depletes world | M1 | Must | Engine | P4 | M | Yes | Not started | No
FR-ECO-02 | Economy | Plausibility-based loot distribution | M1 | Must | Content | P4 | M | Yes | Not started | No
FR-ECO-03 | Economy | Search costs time/noise; persists search % | M1 | Must | Engine | P3 | S | Yes | Not started | No
FR-CNT-03 | Content pipeline | Requirements + effects declared in data | M1 | Must | Engine | P1 | M | Yes | Not started | No
FR-UI-01 | UI | Story-first single-decision primary screen | M1 | Must | UI | P1 | M | Yes | Not started | No
FR-UI-02 | UI | Critical stats only; infection as symptoms | M1 | Must | UI | P4 | S | No | Not started | No
FR-UI-03 | UI | Choices show known costs; no fake choice | M1 | Must | UI | P4 | S | No | Not started | No
FR-UI-05 | UI | Mobile-first one-hand layout | M1 | Must | UI | P1 | M | Yes | Not started | No
NFR-ACC-01 | Accessibility | Critical info without colour/audio alone | M1 | Must | UI | P1 | S | No | Not started | No
NFR-ACC-02 | Accessibility | Full screen-reader support | M1 | Must | UI | P1 | M | Yes | Not started | No
NFR-ACC-03 | Accessibility | Scalable text + high-contrast themes | M1 | Must | UI | P1 | S | Yes | Not started | No
NFR-PERF-01 | Performance | Turn resolves+renders < 100 ms on mid phone | M1 | Must | Engine | P1 | M | No | Not started | No
NFR-PLAT-01 | Platform | Runs in evergreen mobile+desktop browsers | M1 | Must | Client | P1 | M | Yes | Not started | No
NFR-PLAT-03 | Platform | Playable offline for a session | M1 | Should | Client | P1 | S | Yes | Not started | No
NFR-SAVE-01 | Saves | Save = serialized state; lossless resume | M1 | Must | Engine | P1 | M | Yes | Not started | No
NFR-SAVE-02 | Saves | Versioned saves + migration from first format | M1 | Must | Engine | P1 | M | Yes | Not started | No
NFR-MAINT-01 | Maintainability | Content authorable without engine changes | M1 | Must | Engine | P1 | M | No | Not started | No
FR-SIM-01 | World sim | Six state layers independently updatable | M2 | Must | Engine | P1 | M | Yes | Not started | No
FR-SIM-03 | World sim | Regional threat/density/loot evolve off-screen | M2 | Must | Engine | P3 | M | Yes | Not started | No
FR-SIM-05 | World sim | Weather with multi-system effects | M2 | Should | Engine | P4 | M | Yes | Not started | No
FR-SIM-07 | World sim | Zombie population + migrating hordes | M2 | Must | Engine | P1 | L | Yes | Not started | No
FR-SIM-08 | World sim | Global infrastructure decay | M2 | Should | Engine | P3 | M | Yes | Not started | No
FR-SIM-09 | World sim | Other survivor groups simulated off-screen | M2 | Should | Engine | P5 | M | Yes | Not started | No
FR-SIM-10 | World sim | Apocalypse Director biases pacing | M2 | Must | Engine | P1 | L | Yes | Not started | No
FR-SIM-11 | World sim | Living History append-only event log | M2 | Should | Engine | P3 | M | Yes | Not started | No
FR-MAP-04 | Exploration | Route conditions change with world state | M2 | Should | Engine | P4 | S | Yes | Not started | No
FR-INJ-03 | Injuries | Bleeding ticks; deep cut leaves scent trail | M2 | Should | Engine | P2 | M | Yes | Not started | No
FR-CBT-06 | Combat | Zombie state machine driven by senses | M2 | Must | Engine | P1 | L | Yes | Not started | No
FR-CBT-07 | Combat | Distinct zombie types (Screamer, Stalker) | M2 | Should | Engine | P1 | M | Yes | Not started | No
FR-CBT-08 | Combat | Hordes routed/funnelled, not out-traded | M2 | Should | Engine | P4 | M | Yes | Not started | No
NFR-PERF-02 | Performance | Per-tick cost bounded; heavy updates amortized | M2 | Should | Engine | P1 | M | Yes | Not started | No
NFR-PRIV-01 | Privacy | Minimal data; opt-in telemetry; no PII | M2 | Must | Infra | P1 | S | No | Not started | No
PROD-08 | Instrumentation | Telemetry instrumentation (PRD §4 proxies) | M2 | Should | Infra | P1 | M | Yes | Not started | No
FR-MAP-06 | Exploration | Claimable safehouse node; can be lost | M3 | Must | Engine | P3 | S | Yes | Not started | No
FR-INJ-09 | Injuries | Mind model surfaced via behaviour, not bars | M3 | Should | Engine | P5 | M | Yes | Not started | No
FR-CBT-09 | Combat | Fear Meter + panic degrade options at extremes | M3 | Should | Engine | P2 | M | Yes | Not started | No
FR-CBT-10 | Combat | Last Stand: terminal combat as final-choice scene | M3 | Should | Design | P2 | M | Yes | Not started | No
FR-SHL-01 | Shelter | One evolving home shelter | M3 | Must | Engine | P5 | L | Yes | Not started | No
FR-SHL-02 | Shelter | Daily report of off-screen community activity | M3 | Must | Engine | P5 | M | Yes | Not started | No
FR-SHL-06 | Shelter | Night attacks as defensive scenes with losses | M3 | Must | Engine | P4 | M | Yes | Not started | No
FR-SHL-10 | Shelter | Shelter can be lost (overrun/burned/abandoned) | M3 | Must | Engine | P3 | M | Yes | Not started | No
FR-NPC-01 | Survivors | Handcrafted survivor pool (M3 subset → grows to M4) | M3 | Must | Content | P5 | XL | Yes | Not started | No
FR-NPC-03 | Survivors | Recruitable companions, autonomous AI | M3 | Must | Engine | P5 | L | Yes | Not started | No
FR-NPC-04 | Survivors | Permanent companion death, remembered | M3 | Must | Engine | P5 | M | Yes | Not started | No
FR-NPC-09 | Survivors | Storyteller surfaces relationship/history threads | M3 | Should | Engine | P5 | M | Yes | Not started | No
FR-STY-07 | Story | Authored failure endings with closure | M3 | Must | Content | P2 | M | Yes | Not started | No
PROD-10 | Playtest | External playtest program (starts at Fun Gate) | M3 | Must | QA | P1 | M | No | Not started | No
FR-CORE-06 | Core loop | Inline micro-choices at low/zero cost | M4 | Should | Engine | P4 | S | Yes | Not started | No
FR-MAP-05 | Exploration | Map-as-journal: player notes + auto-annotation | M4 | Should | UI | P3 | M | Yes | Not started | No
FR-PLR-05 | Player | Artifact metadata (provenance/history) | M4 | Should | Engine | P6 | M | Yes | Not started | No
FR-PLR-06 | Player | Durability: gear wears, jams, breaks, repairs | M4 | Should | Engine | P6 | S | Yes | Not started | No
FR-PLR-07 | Player | Skills improve narrowly through use | M4 | Should | Engine | P6 | M | Yes | Not started | No
FR-INJ-02 | Injuries | Wound severity tiers | M4 | Should | Engine | P2 | S | Yes | Not started | No
FR-INJ-05 | Injuries | Infection as staged identity (no bar) | M4 | Must | Engine | P2 | L | Yes | Not started | No
FR-INJ-06 | Injuries | Infection alters perception/dialogue/symptoms | M4 | Should | Content | P2 | M | Yes | Not started | No
FR-INJ-07 | Injuries | Diagnosis / treatment / quarantine paths | M4 | Should | Engine | P2 | M | Yes | Not started | No
FR-INJ-08 | Injuries | No instant Game Over on infection | M4 | Must | Design | P2 | S | No | Not started | No
FR-ENC-03 | Encounters | Encounter chains (flags enable follow-ups) | M4 | Should | Content | P1 | M | Yes | Not started | No
FR-ENC-04 | Encounters | Multi-stage encounters | M4 | Should | Content | P1 | M | Yes | Not started | No
FR-ENC-05 | Encounters | Full category coverage | M4 | Must | Content | P1 | L | Yes | Not started | No
FR-ENC-06 | Encounters | Moral encounters feeding Humanity | M4 | Should | Content | P5 | M | Yes | Not started | No
FR-ENC-07 | Encounters | False encounters (tension, no payoff) | M4 | Could | Content | P1 | S | Yes | Not started | No
FR-ENC-08 | Encounters | Encounter evolution by node state | M4 | Should | Content | P3 | M | Yes | Not started | No
FR-ENC-10 | Encounters | Director can inject a pacing beat | M4 | Should | Engine | P1 | S | Yes | Not started | No
FR-CBT-03 | Combat | Improvised/environmental actions | M4 | Should | Engine | P4 | M | Yes | Not started | No
FR-ECO-04 | Economy | Four resource loops with drains + sinks | M4 | Should | Engine | P4 | M | Yes | Not started | No
FR-ECO-05 | Economy | Food spoilage + water purification | M4 | Should | Engine | P4 | S | Yes | Not started | No
FR-ECO-06 | Economy | Crafting gated by blueprints/components/rooms | M4 | Should | Engine | P6 | L | Yes | Not started | No
FR-ECO-07 | Economy | Repairs keep artifacts alive | M4 | Should | Engine | P6 | S | Yes | Not started | No
FR-ECO-09 | Economy | Hidden loot rewarding curiosity + NPC hints | M4 | Should | Content | P5 | M | Yes | Not started | No
FR-SHL-03 | Shelter | Assignable jobs run while away | M4 | Should | Engine | P5 | M | Yes | Not started | No
FR-SHL-04 | Shelter | Craftable rooms unlock capability | M4 | Should | Engine | P5 | M | Yes | Not started | No
FR-SHL-05 | Shelter | Generator on scarce fuel powers rooms | M4 | Could | Engine | P4 | S | Yes | Not started | No
FR-SHL-07 | Shelter | Hope-vs-survival: cold-optimal bleeds morale | M4 | Should | Design | P5 | M | No | Not started | No
FR-NPC-02 | Survivors | Per-character memory (trust/respect/fear) | M4 | Must | Engine | P5 | L | Yes | Not started | No
FR-NPC-05 | Survivors | Desertion + betrayal from low trust | M4 | Should | Engine | P5 | M | Yes | Not started | No
FR-NPC-06 | Survivors | Conversations as real loot/location hints | M4 | Must | Engine | P5 | L | Yes | Not started | No
FR-NPC-07 | Survivors | Inter-NPC relationships affect morale | M4 | Should | Engine | P5 | M | Yes | Not started | No
FR-STY-01 | Story | Three story layers (yours/city/truth) | M4 | Should | Content | P5 | M | Yes | Not started | No
FR-STY-02 | Story | Story events fire on world conditions | M4 | Must | Engine | P1 | M | Yes | Not started | No
FR-STY-03 | Story | Radio network: evolving signal types | M4 | Should | Content | P5 | L | Yes | Not started | No
FR-UI-04 | UI | Depth screens on demand | M4 | Must | UI | P6 | L | Yes | Not started | No
FR-UI-06 | UI | Emotional UI + Quiet Screen for loss | M4 | Should | UI | P2 | M | Yes | Not started | No
FR-AUD-01 | Audio | Layered state-driven adaptive mix | M4 | Should | Audio | P1 | L | Yes | Not started | No
FR-AUD-02 | Audio | Audio as information | M4 | Should | Audio | P1 | M | Yes | Not started | No
FR-AUD-03 | Audio | Deliberate silence + adaptive music | M4 | Should | Audio | P1 | M | Yes | Not started | No
FR-AUD-06 | Audio | Non-audio equivalent for every sound cue | M4 | Must | UI | P1 | M | Yes | Not started | No
FR-CNT-04 | Content pipeline | Rule of Three for significant locations | M4 | Should | Content | P1 | M | Yes | Not started | No
NFR-ACC-04 | Accessibility | Reduced-motion / reduced-flicker modes | M4 | Should | UI | P1 | XS | Yes | Not started | No
NFR-LOC-01 | Localization | All player-facing strings externalized | M4 | Should | Engine | P1 | S | Yes | Not started | No
PROD-11 | Art/Audio | Art + audio direction locked | M4 | Should | Art | P1 | M | No | Not started | No
FR-MAP-07 | Exploration | Vehicles change travel economy | M5 | Could | Engine | P4 | M | Yes | Not started | No
FR-MAP-08 | Exploration | Fast travel between known safe nodes | M5 | Could | Engine | P4 | S | Yes | Not started | No
FR-PLR-08 | Player | Unlockable starting backgrounds | M5 | Could | Content | P6 | S | Yes | Not started | No
FR-PLR-09 | Player | Legacy progression broadens starts | M5 | Could | Engine | P6 | M | Yes | Not started | No
FR-INJ-10 | Injuries | Hidden Humanity influences endings/loyalty | M5 | Could | Engine | P5 | M | Yes | Not started | No
FR-INJ-11 | Injuries | Scars persist; NPCs reference them | M5 | Could | Content | P2 | S | Yes | Not started | No
FR-ENC-09 | Encounters | Rare + legendary gated encounters | M5 | Could | Content | P1 | S | Yes | Not started | No
FR-ECO-08 | Economy | Trading at scarcity/reputation prices | M5 | Could | Engine | P5 | M | Yes | Not started | No
FR-ECO-10 | Economy | Balance preserves the "last can" moment | M5 | Should | Design | P4 | M | No | Not started | No
FR-SHL-08 | Shelter | Memorial wall records the dead | M5 | Could | Content | P5 | S | Yes | Not started | No
FR-SHL-09 | Shelter | Emergent community identity read by others | M5 | Could | Engine | P5 | M | Yes | Not started | No
FR-NPC-08 | Survivors | Personal quests; optional romance | M5 | Could | Content | P5 | L | Yes | Not started | No
FR-NPC-10 | Survivors | Survivor groups/factions with diplomacy | M5 | Could | Engine | P5 | L | Yes | Not started | No
FR-STY-04 | Story | Player broadcasting with consequences | M5 | Could | Engine | P4 | M | Yes | Not started | No
FR-STY-05 | Story | Rumor system: variably-reliable leads | M5 | Could | Engine | P5 | M | Yes | Not started | No
FR-STY-06 | Story | Multiple endings from run components | M5 | Must | Design | P1 | L | Yes | Not started | No
FR-STY-08 | Story | Epilogues following surviving NPCs | M5 | Should | Content | P5 | M | Yes | Not started | No
FR-STY-09 | Story | Living History surfaces in later runs | M5 | Could | Engine | P3 | M | Yes | Not started | No
FR-UI-07 | UI | Keyboard/controller parity with touch | M5 | Should | UI | P1 | S | Yes | Not started | No
FR-AUD-04 | Audio | Radio sonic identity per signal type | M5 | Could | Audio | P5 | S | Yes | Not started | No
FR-AUD-05 | Audio | Dynamic audio memory in dreams/quiet screens | M5 | Could | Audio | P2 | S | Yes | Not started | No
FR-CNT-05 | Content pipeline | Mod-friendly structure (capability) | M5 | Could | Engine | P1 | S | Yes | Not started | No
NFR-REL-01 | Reliability | Crash-free ≥ 99.5%; repro from seed+state | M5 | Must | QA | P1 | L | Yes | Not started | No
NFR-LOC-02 | Localization | Text-expansion tolerance; RTL considered | M5 | Could | UI | P1 | S | Yes | Not started | No
PROD-09 | Balance | Staged balance passes (GDD XVI) | M5 | Must | Design | P4 | L | No | Not started | No
PROD-12 | Saves | Save migration proven across a schema change | M5 | Must | QA | P1 | M | Yes | Not started | No

## Content Budget
Content Budget
Caps that protect REVIEW CAPACITY. Set the current milestone; a red Headroom = stop authoring, go playtest.
Current milestone: | M1 |  | ← change this; caps & headroom update automatically
Content type | Cap (this milestone) | Actual (update) | Headroom | Status | type | M1 | M2 | M3 | M4 | M5
Regions | 1 | 0 | 1 | 1 left | Regions | 1 | 1 | 1 | 6 | 6
Nodes | 8 | 0 | 8 | 8 left | Nodes | 8 | 8 | 8 | 60 | 60
Survivors | 1 | 0 | 1 | 1 left | Survivors | 1 | 1 | 5 | 100 | 100
Companions | 0 | 0 | 0 | none this milestone | Companions | 0 | 0 | 1 | 6 | 6
Zombie types | 2 | 0 | 2 | 2 left | Zombie types | 2 | 4 | 4 | 8 | 8
Encounters | 20 | 0 | 20 | 20 left | Encounters | 20 | 35 | 60 | 250 | 250
Radio stations | 0 | 0 | 0 | none this milestone | Radio stations | 0 | 0 | 2 | 8 | 8
Items | 15 | 0 | 15 | 15 left | Items | 15 | 20 | 30 | 120 | 120
Weapons | 6 | 0 | 6 | 6 left | Weapons | 6 | 8 | 10 | 40 | 40
Going over a cap is NOT resolved by adding hours — cut Shoulds/Coulds or push the excess to the next milestone. Caps = one person’s review capacity. M5 = freeze (no new content).
Note on H6: Numeric caps (upper bounds) the table looks up. Edit here to change budgets.

## Risk Burn-down
Risk Burn-down
Each PRD risk mapped to the milestone that retires it. Risk reduction is scheduled, not hoped for.
Risk | Impact | Likelihood | Retired / managed at | How | Status
Undecided stack stalls delivery | Med | Med | M0 | Time-boxed ADR-0001; decide and move | Open
Systemic but not fun | High | Med | M3 Fun Gate | Prove the slice grips before any content pour | Open
Impressive but static world | High | Med | M2 | Off-screen evolution + director = reactive turns | Open
Content volume / repetition | High | High | M4 (continuous) | AI-at-volume behind review cap; recombination, Rule of Three, cooldowns; measure repeat rate | Open
Scope creep | High | High | every boundary | Cut filter + Won’t-now register + parking-lot change control | Open
Balance fragility | Med | Med | M5 (staged passes) | Director + comeback mechanics; telemetry on death timing/causes/margins | Open
Infection-as-identity confusing | Med | Med | M4 | Strong symptoms + optional diagnosis; comprehension-tested | Open
Accessibility retrofit | Med | Low | from M1 | NFR-ACC as Must from the first UI; never bolted on late | Open
Save-schema churn | Med | Med | M1 onward | Versioned saves + migration from the first save format | Open
Solo review-capacity overload | High | Med | every milestone | Content budget caps generation to what one person can gate | Open

## Decision Gates
Decision Gates (ADRs)
Open decisions tied to the milestone they must be resolved by. ADR-0001 is the one to force.
ADR / decision | Question | Resolve by | Blocks if open | Decision / status
ADR-0001 | Engine language & runtime | M0 (time-boxed) | ALL code — top stall risk | Open
ADR-0002 | Content data format (JSON/YAML/custom) | M0 | Content authoring tooling | Open
ADR-0003 | Save storage & versioning | M1 | Save migration design | Open
ADR-0004 | Platform ordering (native/Steam/bot) | M4 | Post-launch client work | Open
Monetization | Premium / free+cosmetic / episodic | M5 | Launch planning | Open
Cross-run memory | How much Living History carries between runs | M4 | Endings & meta-progression | Open
Metric thresholds | Exact PRD §4 numeric targets | after M2 telemetry | Balance sign-off | Open
Licensing | Proprietary / source-available / open | before public beta (M4) | Public distribution | Open

## Parking Lot
Parking Lot & Won’t-Now Register
New ideas land HERE, never in a live milestone. Triage only at boundaries. Won’t-now items are frozen.
Idea / feature | Source | Serves a principle? | Decision | Reason | Triage milestone
Multiplayer / PvP | PRD §6 Won’t-now | No (breaks single-player focus) | Won’t-now (frozen) | Out of scope for v1.0; not required to prove the game | —
UGC / mod marketplace | PRD §6 | Partial (P1 content-as-data) | Won’t-now (frozen) | Capability yes (FR-CNT-05 Could), storefront no | post-launch
Cities beyond the launch city | PRD §6 | Yes (P3) | Won’t-now (frozen) | One city proves the game; more is post-launch | post-launch
Full faction territory wars | PRD §6 | Yes (P5) | Won’t-now (frozen) | Depth trap; factions ship shallow at v1 (FR-NPC-10 Could) | post-launch
Animal ecosystems | PRD §6 | Weak | Won’t-now (frozen) | No principle strongly served; recorded, not cut | —
Deep vehicle modification | PRD §6 | Weak (P4) | Won’t-now (frozen) | Vehicles are Could (FR-MAP-07); modification depth is not | —
Live-service / always-online | PRD §3 non-goal | No | Won’t-now (frozen) | Contradicts offline-capable, no-treadmill goal | —
(capture new ideas below — do not add to a live milestone) |  |  | Parked |  | next boundary

## Fun-Gate Log
Fun-Gate Log
Every gate verdict. The retellable moment is the evidence. The gate governs scope.
Date | Stage | Milestone | Build / seed | Retellable moment? (what) | "One more day"? | Decision
| Loop-Feel Check | M1
| SLICE FUN GATE | M3
| "one more day" (external) | M5